## Slide 1
Improved cell (reduced R)
Circulate full v1.0 lattice
End-to-end tracking
Error studies
Determine vac. chamber inner wall size
Mechanically feasible vac. chamber
Magnet pole clearance requirement
Corrector coil requirements
Field quality requirements
Magnet design
Design and integration of BPMs
Pipe and collective effects
Design corrector coils
Corrector coil power supplies
Fix position of linac, injector
Girder vibration requirement
Correction studies
BPM requirements
BPM readout electronics
Pumping, getter system
Support structure
Mechanical design of full girder
Control system
Correction algorithms
Cb Task Map
Not a WBS, shows dependencies
Does not include backtracking/loops
Incomplete!
Existing plan for linac commissioning
Shielding blocks layout
Pipe and collective effects
Correction studies
Shielding blocks layout
Prototype magnet(s)
Vacuum requirements