## Rate
Date |  |  |  |  | Number of rotating coil measurements
Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Sum | Notes
2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 |  |  |  |  | 2 | 2 | Batch only arrived Friday p.m.
2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 3 | 3 | Holiday | 4 | 0 | 10 | John C. on vacation this week, only Toby. Also PC software issue on Friday
2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 4 | 3 | 5 | 5 | 4 | 21
2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 5 | 7 | 4 | 4 | 2 | 22 | John C. out on Friday
2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 5 | 2 | 5 | 6 | 5 | 23 | Most of survey group out this week (just Chenghao)
2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 7 | 5 | 7 | 5 | 6 | 30
2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 7 | 8 | 7 | 7 | 6 | 35
2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 8 | 7 | 3 | 10 | 9 | 37 | SJB out Weds, Thurs a.m.
2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 6 | 9 | 8 | 9 | 0 | 32 | John C. out on Friday (probably Toby too)
2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 6 | 7 | 6 | 8 | 4 | 31 | Ming out this week, survey group busy
2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 | Holiday | 4 | 8 | 10 | 6 | 28 | John C. out on Tuesday
2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 7 | 7 | 6 | 6 | 7 | 33
2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 3 | 6 | 5 | 2 | 2 | 18 | started to wait for BD crate delivery
2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 3 | 2 | 2 | 5 | 6 | 18 | John C.'s coil (#76) electronics broken Weds-Fri (also sort of waiting for BD delivery)
2018-10-01 |  |  |  |  | 5
Formulas:
Tuesday = [Monday]+1
Tuesday = [Tuesday, row above]+7
Wednesday = [Tuesday]+1
Monday = [Monday, row above]+7

## Redos
Magnet type | Total magnets | Percent redos | Redos | Number accepted (2000 series) |  | Remaining | Redos
QF | 107 | 55% | 58.85 | 91 | 85.05% | 16 | 8.8
QD | 27 | 32% | 8.64 | 27 | 100% | 0 | 0
BD | 32 | 66.67% | 21.3333 | 10 | 31.25% | 22 | 14.6667
BDT1 | 28 | 50% | 14 | 2 | 7.143% | 26 | 13
BDT2 | 20 | 50% | 10 | 2 | 10% | 18 | 9
Total | 214 | 52.72% | 112.8233 | 132 | 61.68% | 82 | 45.4667 | 55.45%

## Model (simple)
10.231 | magnets per week |  | 2 | coil benches | 55.45% | iteration re-dos | 5 | working days per week
Rotating coil measurements |  |  |  |  | 10 | weeks between unrecoverable calibration slips (on any given coil)
10.231 | first measurements
5.6728 | extra iterations
10.231 | final iterations
2 | additional E4E measurements per week (one per coil bench)
0.8231 | Extra measurements due to calibration slips
28.9579 | total coil measurements per week
5.7916 | coil measurements per day
2.8958 | coil measurements per bench per day
Magnet surveys at bench
10.231 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
0.8231 | Extra surveys due to calibration slips
13.0541 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10.231 | per week
2.0462 | per day
Schedule
214 | Total magnets
132 | Magnets done
82 | Magnets remaining
8.0148 | weeks to complete (no contingency)
Current date | 2018-10-01
End date | 2018-11-26 02:30
Goal | 2018-11-30 | -6.493% | speed-up needed

## Model
9.12 | magnets per week |  | 2 | coil benches | 55.45% | iteration re-dos | 5 | working days per week
Rotating coil measurements |  |  |  |  | 10 | weeks between unrecoverable calibration slips (on any given coil)
9.12 | first measurements
5.0568 | extra iterations
9.12 | final iterations
2 | additional E4E measurements per week (one per coil bench)
0.712 | Extra measurements due to calibration slips
26.0088 | total coil measurements per week
5.2018 | coil measurements per day
2.6009 | coil measurements per bench per day
Magnet surveys at bench
9.12 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
0.712 | Extra surveys due to calibration slips
11.832 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
9.12 | per week
1.824 | per day
Schedule
214 | Total magnets
132 | Magnets done
82 | Magnets remaining
8.9912 | weeks to complete (no contingency)
Current date | 2018-10-01
End date | 2018-12-02 22:32
Goal | 2018-11-30 | 4.898% | speed-up needed

## Example model
8 | magnets per week | 2 | coil benches | 25% | iteration re-dos | 5 | working days per week
Rotating coil measurements
8 | first measurements
10 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20 | total coil measurements per week
4 | coil measurements per day
2 | coil measurements per bench per day
Magnet surveys at bench
8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
10 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
10 | per week
2 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
25.25 | weeks to complete (no contingency)
Start date | 2018-07-02
End date | 2018-12-25 18:00

## Example week
|  | Coil measurements | [8 empty] | Shim packs |  | Survey
|  | Initial measurement |  | First iterations |  | Extra iterations |  | E4E calibration |  | Per day |  | Per day |  | Per day
|  | John | Toby | John | Toby | John | Toby | John | Toby |  | Henry, Toby, others |  | Survey group
Monday | AM | 1 | 1
| PM | 1 | 1 | [6 empty] | 4 | 1 | 1 |  | 0
Tuesday | AM | 1 | 1 | [7 empty] | 1
| PM | 1 | 1 | [6 empty] | 4 | 2 | 3 |  | 0
Wednesday | AM |  |  | 1 | 1 | [5 empty] | 2 |  | 2
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 2 | 4 | 2 | 4
Thursday | AM |  |  | 1 | 1 | [5 empty] | 1 |  | 1
| PM |  |  | 1 | 1 |  |  |  |  | 4 | 1 | 2 | 1 | 2
Friday | AM |  |  |  |  | 1 | 1 | [5 empty] | 2
| PM | [6 empty] | 1 | 1 | 4 |  | 0 | 2 | 4
[9 empty] | 20 |  | 10 |  | 10

## Pessimistic model
7 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
7 | first measurements
11.2 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
20.2 | total coil measurements per week
4.04 | coil measurements per day
2.02 | coil measurements per bench per day
Magnet surveys at bench
7 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
9 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
11.2 | per week
2.24 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
28.8571 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
37.5143 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2019-03-21 14:24

## Pessimistic fixed
10.8 | magnets per week | 2 | coil benches | 60% | iteration re-dos | 5 | working days per week
Rotating coil measurements
10.8 | first measurements
17.28 | iteration measurements
2 | additional E4E measurements per week (one per coil bench)
30.08 | total coil measurements per week
6.016 | coil measurements per day
3.008 | coil measurements per bench per day
Magnet surveys at bench
10.8 | surveys finishing a magnet
2 | additional E4E surveys (one per coil bench)
12.8 | surveys per week
(probably ~4 per day in the latter half of the week)
Tuning wire holder fabrication
17.28 | per week
3.456 | per day
Schedule
216 | Total magnets
14 | Magnets done
202 | Magnets remaining
18.7037 | weeks to complete (no contingency)
30% | Contingency because they get distracted by other projects
24.3148 | weeks to complete (incl. contingency)
Start date | 2018-07-02
End date | 2018-12-19 04:53